## Sheet1
Agile Project Plan
Project Name | APIC
Project Manager | ######
Project Deliverable | ######
Scope Statement | ######
Start Date | 2018-03-04
End Date | 2016-10-05
Overall Progress | 20%
Task Name | Responsible | Start | End | Days | Status
Splash Screen |  | 2018-03-05 | 2018-03-08 | 3
design interface | Nermeen Mohamed | 2018-03-05 | 2018-03-06 | 5hour | complete
design logo | Manal Taha | 2018-03-05 | 2018-03-06 | 3hour | complete
implement progress bar | Heba Gharib | 2018-03-06 | 2018-03-07 | 4hour | complete
implement code | Mohamed Anwer | 2018-03-06 | 2018-03-07 | 1 | complete
test the splash screen | Sara mohamed | 2018-03-07 | 2018-03-08 | 1 | complete
Sign up |  | 2018-03-09 | 2018-03-13 | 4 | complete
data analysis and requirement gathering | Nermeen Mohamed | 2018-03-09 | 2018-03-10 | 1 | complete
design interface | Ola el sayed | 2018-03-10 | 2018-03-11 | 1 | complete
create table in database | Manal Taha | 2018-03-11 | 2018-03-12 | 3hour | complete
write code for the button(sign up) | Mohamed Anwer | 2018-03-11 | 2018-03-12 | 5hour | complete
connect code of the sign up button with database | Sara mohamed | 2018-03-12 | 2018-03-13 | 4hour | complete
link the sign up page with splash | Mohamed Anwer | 2018-03-12 | 2018-03-13 | 5hour | complete
let the tester to try the button | Heba Gharib | 2018-03-12 | 2018-03-13 | 5hour | complete
log in |  | 2018-03-14 | 2018-03-18 | 4 | complete
data analysis and requirement gathering | Heba Gharib | 2018-03-14 | 2018-03-15 | 1 | complete
design interface | Sara mohamed | 2018-03-15 | 2018-03-16 | 1 | complete
write code for the button(log in) | Nermeen Mohamed | 2018-03-16 | 2018-03-17 | 3hour | complete
connect code of the sign up button with database | Mohamed Anwer | 2018-03-16 | 2018-03-17 | 5hour | complete
link the log in page with splash page | Manal Taha | 2018-03-17 | 2018-03-18 | 4hour | complete
let the tester to try the button | Ola el sayed | 2018-03-17 | 2018-03-18 | 3hour | complete
home page |  | 2018-03-18 | 2018-03-25 | 7 | In progress
data analysis and requirement gathering | Ola el sayed | 2018-03-18 | 2018-03-19 | 1 | In progress
design interface of home page | Manal Taha | 2018-03-19 | 2018-03-20 | 1 | In progress
design menue for active people | Sara mohamed | 2018-03-19 | 2018-03-20 | 1 | In progress
design menue for other pages | Nermeen Mohamed | 2018-03-20 | 2018-03-21 | 1 | In progress
design the reacts for posts | Heba Gharib | 2018-03-20 | 2018-03-21 | 1 | In progress
write code for home page | Mohamed Anwer | 2018-03-21 | 2018-03-22 | 1 | not started
write code for menue of other pages | Manal Taha | 2018-03-21 | 2018-03-22 | 1 | not started
write code for active people menue | Ola el sayed | 2018-03-22 | 2018-03-23 | 1 | not started
write code for reacts | Mohamed Anwer | 2018-03-22 | 2018-03-23 | 1 | not started
link the homepage with previous pages | Nermeen Mohamed | 2018-03-23 | 2018-03-24 | 1 | not started
test the home page | Sara mohamed | 2018-03-24 | 2018-03-25 | 1 | not started
chat box |  | 2018-04-01 | 2018-04-05 | 4 | not started
data analysis and requirement gathering | Sara mohamed | 2018-04-01 | 2018-04-01 | 5hour | not started
design chat box | Ola el sayed | 2018-04-01 | 2018-04-01 | 4hour | not started
write code for chat box | Mohamed Anwer | 2018-04-02 | 2018-04-03 | 6hour | not started
write code for chat coloring | Nermeen Mohamed | 2018-04-02 | 2018-04-03 | 3hour | not started
write code to change chat neme | Sara mohamed | 2018-04-03 | 2018-04-04 | 2hour | not started
write code to block annoyed users | Manal Taha | 2018-04-03 | 2018-04-04 | 4hour | not started
link chat box with other pages | Heba Gharib | 2018-04-05 | 2018-04-06 | 3hour | not started
test chat box | Ola el sayed | 2018-04-05 | 2018-04-06 | 5hour | not started