## Sheet1
sprint week1(splash screen)
day | date | tasks | Responsible | statue
Monday | 2018-03-05 | design interface | Nermeen Mohamed | complete
Monday | 2018-03-06 | design logo | Manal Taha | complete
Tuesday | 2018-03-06 | implement progress bar | Heba Gharib | complete
wednesday | 2018-03-07 | implement code | Mohamed Anwer | complete
wednesday | 2018-03-08 | test the splash screen | Sara mohamed | complete
sprint week 2(sign up page)
day | date | tasks | Responsible | statue
Friday | 2018-03-09 | data analysis and requirement gathering | Nermeen Mohamed | complete
Saturday | 2018-03-10 | design interface | Ola el sayed | complete
Sunday | 2018-03-11 | create table in database | Manal Taha | complete
Sunday | 2018-03-11 | write code for the button(sign up) | Mohamed Anwer | complete
Monday | 2018-03-12 | connect code of the sign up button with database | Sara mohamed | complete
Monday | 2018-03-12 | link the sign up page with splash | Mohamed Anwer | complete
Monday | 2018-03-12 | let the tester to try the button | Heba Gharib | complete
sprint week 3(log in page)
day | date | tasks | Responsible | statue
Wednesday | 2018-03-14 | data analysis and requirement gathering | Heba Gharib | complete
Thursday | 2018-03-15 | design interface | Sara mohamed | complete
Friday | 2018-03-16 | write code for the button(log in) | Nermeen Mohamed | complete
Friday | 2018-03-16 | connect code of the sign up button with database | Mohamed Anwer | complete
Saturday | 2018-03-17 | link the log in page with splash page | Manal Taha | complete
Saturday | 2018-03-17 | let the tester to try the button | Ola el sayed | complete
sprint week 4 (home page)
day | date | tasks | Responsible | statue
sunday | 2018-03-18 | data analysis and requirement gathering | Ola el sayed | in progress
monday | 2018-03-19 | design interface of home page | Manal Taha | in progress
monday | 2018-03-19 | design menue for active people | Sara mohamed | in progress
Tuesday | 2018-03-20 | design menue for other pages | Nermeen Mohamed | in progress
Tuesday | 2018-03-20 | design the reacts for posts | Heba Gharib | in progress
wednesday | 2018-03-21 | write code for home page | Mohamed Anwer | not started
wednesday | 2018-03-21 | write code for menue of other pages | Manal Taha | not started
Thursday | 2018-03-22 | write code for active people menue | Ola el sayed | not started
Thursday | 2018-03-22 | write code for reacts | Mohamed Anwer | not started
Friday | 2018-03-23 | link the homepage with previous pages | Nermeen Mohamed | not started
Saturday | 2018-03-24 | test the home page | Sara mohamed | not started
sprint week 5 (chat box)
day | date | tasks | Responsible | statue
Sunday | 2018-04-01 | data analysis and requirement gathering | Ola el sayed | not started
Sunday | 2018-04-01 | design chat box | Manal Taha | not started
Monday | 2018-04-02 | write code for chat box | Sara mohamed | not started
Monday | 2018-04-02 | write code for chat coloring | Nermeen Mohamed | not started
Tuesday | 2018-04-03 | write code to change chat neme | Heba Gharib | not started
Tuesday | 2018-04-03 | write code to block annoyed users | Mohamed Anwer | not started
Wednesday | 2018-04-05 | link chat box with other pages | Manal Taha | not started
Wednesday | 2018-04-05 | test chat box | Ola el sayed | not started